## Cover Page
BAGISTO 2.4 – SOFTWARE QUALITY ASSURANCE
Complete SQA Documentation Package
Project URL | https://github.com/bagisto/bagisto
Technology Stack | Laravel + MySQL
Admin Email | admin@example.com
Admin Password | admin123
Customer Email | ahnattanha562@gmail.com
Customer Password | 12345678
Prepared By | SQA Engineer
Version | v1.0
Total Requirements | 46
Total Test Scenarios | 46
Total Test Cases | 155 Test Cases
Document Set | Test Plan, Requirement Analysis, RTM, Test Scenarios, Test Cases, Bug Report, Test Summary Report
Contents of this Workbook
1. Test Plan
2. Requirement Analysis
3. Requirement Traceability Matrix (RTM)
4. Module Overview
5. Test Scenarios
6. Test Cases
7. Bug Report
8. Test Summary Report

## Test Plan
TEST PLAN – BAGISTO 2.4 E-COMMERCE PLATFORM
1. Document Control
Document Title | Bagisto 2.4 SQA Test Plan
Project | Bagisto 2.4 (Open Source Laravel E-commerce Platform)
Repository | https://github.com/bagisto/bagisto
Prepared By | SQA Engineer
Version | v1.0
Status | Draft
2. Introduction / Objective
Purpose | To define the scope, approach, resources, and schedule of testing activities for the Bagisto 2.4 e-commerce application, ensuring all storefront and admin functionality works as per requirements before release.
Application Under Test | Bagisto 2.4 – Laravel + MySQL based multi-vendor e-commerce platform (storefront + admin panel).
3. Scope of Testing
In Scope | Authentication (login/logout/registration/forgot password), Product Catalog (listing/search/filter/sort/detail/reviews), Shopping Cart, Checkout, Order Management, Admin – Catalog (products/categories/attributes), Admin – Orders, User Management, Admin – Settings (general/tax/shipping/payment), UI/UX & Navigation, and basic Performance checks.
Out of Scope | Multi-vendor marketplace add-ons, payment gateway integrations beyond Cash on Delivery (Stripe/PayPal sandbox flows), third-party API integrations, native mobile apps, load/stress testing beyond basic page-load benchmarks, and automated test scripting (covered in a later phase of the roadmap).
4. Test Approach / Strategy
Testing Levels | System Testing and User Acceptance style functional testing performed on the deployed local application.
Testing Types | Functional, UI/UX, Security (basic – SQL injection / session checks), and Performance (basic page-load timing).
Testing Method | Manual black-box testing using documented Test Scenarios and Test Cases derived from the Requirement Analysis sheet.
Test Design Technique | Equivalence Partitioning and Boundary Value Analysis for input fields; Error Guessing for security/edge cases.
5. Roles & Responsibilities
SQA Engineer | Requirement analysis, test scenario & test case design, test execution, bug reporting, RTM maintenance, and final test summary reporting.
Developer / Dev Team | Fixing reported defects and supporting root-cause analysis.
Project Lead | Reviewing the test plan, prioritizing defects, and sign-off on release readiness.
6. Test Environment
Environment | Local development environment
Technology Stack | Laravel + MySQL
Browsers | Chrome (primary), Firefox, Edge
Devices | Desktop, Tablet (emulated), Mobile (emulated) for responsive checks
Test Accounts | Admin: admin@example.com / admin123 ¦ Customer: ahnattanha562@gmail.com / 12345678
7. Entry Criteria
Criteria | • Application build is deployed and accessible on the test environment. • Requirement Analysis and Test Case documents are reviewed and approved. • Test data (admin/customer accounts, sample products) is available.
8. Exit Criteria
Criteria | • All planned test cases (155) have been executed. • No open Critical or High severity defects remain unresolved. • Test Summary Report is completed and shared with stakeholders. • Pass rate meets the agreed quality threshold (≥ 95% of High priority cases passing).
9. Suspension & Resumption Criteria
Suspension | Testing is suspended if a Critical/Blocker defect prevents further progress (e.g., login broken, checkout fails for all flows).
Resumption | Testing resumes once the blocking defect is fixed, deployed, and verified.
10. Deliverables
Documents | • Test Plan • Requirement Analysis • Requirement Traceability Matrix (RTM) • Test Scenarios • Test Cases • Bug Reports • Test Summary Report
11. Defect Management
Severity Levels | Critical, Major, Minor, Trivial
Priority Levels | High, Medium, Low
Bug Life Cycle | New → Open → Assigned → In Progress → Fixed → Retest → Closed / Reopened
Tracking Tool | Bug Report sheet (this workbook) – to migrate to Jira/TestRail in later roadmap phase
12. Risks & Mitigation
Risk: Limited environment access | Mitigation: Use shared local environment with seeded test data.
Risk: Tight schedule (single SQA engineer) | Mitigation: Prioritize High priority modules (Auth, Cart, Checkout, Orders) first.
Risk: Frequent requirement changes | Mitigation: Keep RTM updated and re-baseline test cases when requirements change.
13. Schedule (High Level)
Requirement Analysis & Test Design | 1–2 days
Test Case Execution | 2–3 days
Bug Reporting & Retesting | 1 day
Test Summary & Sign-off | 0.5 day

## Requirement Analysis
Req ID | Module | Sub-Module | Requirement Description | Priority | Testing Type | Notes
REQ-AUTH-01 | Authentication | Login | Admin and customer login with valid/invalid credentials | High | Functional | Email + password validation
REQ-AUTH-02 |  | Logout | Session ends correctly after logout | High |  | Redirect to login page
REQ-AUTH-03 |  | Registration | New customer account creation with required fields | High |  | Email uniqueness check
REQ-AUTH-04 |  | Forgot Password | Password reset email sent to registered users | Medium |  | Token expiry testing
REQ-AUTH-05 |  | Remember Me | User stays logged in after browser close | Low |  | Cookie persistence
REQ-CATA-01 | Catalog | Product Listing | Products displayed with correct details on storefront | High | Functional | Name, price, image
REQ-CATA-02 |  | Product Search | Search by keyword returns relevant products | High |  | Partial match, case-insensitive
REQ-CATA-03 |  | Product Filter | Filtering by category, price, attribute narrows results | High |  | Multiple filter combos
REQ-CATA-04 |  | Product Detail | Product page shows all attributes, images, price | High |  | Gallery, variants
REQ-CATA-05 |  | Product Sorting | Sort by price, name, newest works correctly | Medium |  | Ascending/descending
REQ-CATA-06 |  | Product Reviews | Customers can submit and view reviews | Medium |  | Rating 1-5 stars
REQ-CATA-07 |  | Category Navigation |  | High |  | Breadcrumb trail
REQ-CART-01 | Cart | Add to Cart | Products added with correct quantity and price | High | Functional | Single and multiple items
REQ-CART-02 |  | Update Quantity | Cart quantity updates reflect correct subtotal | High |  | Min 1, max stock limit
REQ-CART-03 |  | Remove Item | Items removed from cart; cart updates correctly | High |  | Empty cart state
REQ-CART-04 |  | Cart Persistence | Cart preserved after login for guest users | Medium |  | Session merge
REQ-CART-05 |  | Cart Total | Subtotal, tax, shipping calculated correctly | High |  | Price accuracy
REQ-CHEC-01 | Checkout | Guest Checkout | Guest users can complete order without account | High | Functional | Email capture
REQ-CHEC-02 |  | Registered Checkout | Logged-in user checkout with saved address | High |  | Address auto-fill
REQ-CHEC-03 |  | Shipping Address | Valid/invalid address fields validated | High |  | Required fields
REQ-CHEC-04 |  | Shipping Methods | Available shipping methods shown with prices | High |  | Method selection
REQ-CHEC-05 |  | Payment Methods | Cash on delivery and other methods work | High |  | Payment gateway
REQ-CHEC-06 |  | Order Confirmation | Order confirmation page and email sent | High |  | Order ID, summary
REQ-ORDE-01 | Orders | Order History | Customer can view past orders with status | High | Functional | Pagination
REQ-ORDE-02 |  | Order Detail | Order detail page shows all items and tracking | High |  | Invoice link
REQ-ORDE-03 |  | Order Cancellation | Customer can cancel eligible orders | Medium |  | Status-based eligibility
REQ-ORDE-04 |  | Admin Order Mgmt | Admin can view, update, cancel, invoice orders | High |  | Status workflow
REQ-ORDE-05 |  | Invoice Generation | Admin generates downloadable PDF invoice | Medium |  | PDF accuracy
REQ-ADMI-01 | Admin - Catalog | Add Product | Admin creates simple/configurable/virtual product | High | Functional | All product types
REQ-ADMI-02 |  | Edit Product | Admin edits product details; changes reflect on storefront | High |  | Price, stock, image
REQ-ADMI-03 |  | Delete Product | Admin deletes product; removed from storefront | Medium |  | Soft vs hard delete
REQ-ADMI-04 |  | Product Images | Multiple images upload and assign to product | Medium |  | File size, format
REQ-ADMI-05 |  | Category Mgmt | Admin creates/edits/deletes categories | High |  | Hierarchy, parent-child
REQ-ADMI-06 |  | Attributes | Create and assign product attributes/attribute sets | Medium |  | Text, select, boolean
REQ-USER-01 | User Management | Admin Users | Admin creates/edits sub-admin with roles | Medium | Functional | Role-based access
REQ-USER-02 |  | Customer List | Admin views all customers with filters | Medium |  | Search, export
REQ-USER-03 |  | Customer Profile | Admin edits customer info | Medium |  | Address, email
REQ-ADMI-07 | Admin - Settings | General Config | Store name, currency, locale configurable | High | Functional | Multi-locale
REQ-ADMI-08 |  | Tax Rules | Tax rates applied correctly based on rules | High |  | Country-based tax
REQ-ADMI-09 |  | Shipping Config | Shipping zones and rates configured | High |  | Free shipping threshold
REQ-ADMI-10 |  | Payment Config | Payment methods enabled/disabled | High |  | COD, Stripe
REQ-UIUX-01 | UI/UX | Responsive Design | Storefront responsive on mobile, tablet, desktop | High | UI/UX | Bootstrap breakpoints
REQ-UIUX-02 |  | Navigation | Menu links navigate to correct pages | High |  | No broken links
REQ-UIUX-03 |  | Error Pages | 404 and 500 pages display correctly | Medium |  | Custom error views
REQ-PERF-01 | Performance | Page Load | Key pages load within acceptable time | Medium | Performance | < 3 seconds
REQ-PERF-02 |  | Search Speed | Product search returns results quickly | Medium |  | Large catalog test

## RTM
Req ID | Module | Sub-Module | Requirement Description | Priority | Test Scenario ID(s) | Linked Test Case IDs | Coverage Status
REQ-AUTH-01 | Authentication | Login | Admin and customer login with valid/invalid credentials | High | TS-AUTH-01 | TC-AUTH-01 to TC-AUTH-05 | Covered
REQ-AUTH-02 | Authentication | Logout | Session ends correctly after logout | High | TS-AUTH-02 | TC-AUTH-08, TC-AUTH-09, TC-AUTH-16 | Covered
REQ-AUTH-03 | Authentication | Registration | New customer account creation with required fields | High | TS-AUTH-03 | TC-AUTH-10 to TC-AUTH-13 | Covered
REQ-AUTH-04 | Authentication | Forgot Password | Password reset email sent to registered users | Medium | TS-AUTH-04 | TC-AUTH-14, TC-AUTH-15 | Covered
REQ-AUTH-05 | Authentication | Remember Me | User stays logged in after browser close | Low |  |  | Not Covered
REQ-CATA-01 | Catalog | Product Listing | Products displayed with correct details on storefront | High | TS-CAT-01 | TC-CAT-01, TC-CAT-02 | Covered
REQ-CATA-02 | Catalog | Product Search | Search by keyword returns relevant products | High | TS-CAT-02 | TC-CAT-03 to TC-CAT-05 | Covered
REQ-CATA-03 | Catalog | Product Filter | Filtering by category, price, attribute narrows results | High | TS-CAT-03 | TC-CAT-06 to TC-CAT-09 | Covered
REQ-CATA-04 | Catalog | Product Detail | Product page shows all attributes, images, price | High | TS-CAT-05 | TC-CAT-13 to TC-CAT-15 | Covered
REQ-CATA-05 | Catalog | Product Sorting | Sort by price, name, newest works correctly | Medium | TS-CAT-04 | TC-CAT-10 to TC-CAT-12 | Covered
REQ-CATA-06 | Catalog | Product Reviews | Customers can submit and view reviews | Medium | TS-CAT-06 | TC-CAT-16, TC-CAT-17, TC-CAT-18 | Covered
REQ-CATA-07 | Catalog | Category Navigation |  | High |  |  | Not Covered
REQ-CART-01 | Cart | Add to Cart | Products added with correct quantity and price | High | TS-CART-01 | TC-CART-01 to TC-CART-04 | Covered
REQ-CART-02 | Cart | Update Quantity | Cart quantity updates reflect correct subtotal | High | TS-CART-02 | TC-CART-05 to TC-CART-07 | Covered
REQ-CART-03 | Cart | Remove Item | Items removed from cart; cart updates correctly | High | TS-CART-03 | TC-CART-08, TC-CART-09 | Covered
REQ-CART-04 | Cart | Cart Persistence | Cart preserved after login for guest users | Medium |  |  | Not Covered
REQ-CART-05 | Cart | Cart Total | Subtotal, tax, shipping calculated correctly | High | TS-CART-04 | TC-CART-10 to TC-CART-12 | Covered
REQ-CHEC-01 | Checkout | Guest Checkout | Guest users can complete order without account | High | TS-CHK-01 | TC-CHK-01, TC-CHK-02 | Covered
REQ-CHEC-02 | Checkout | Registered Checkout | Logged-in user checkout with saved address | High | TS-CHK-02 | TC-CHK-03 | Covered
REQ-CHEC-03 | Checkout | Shipping Address | Valid/invalid address fields validated | High | TS-CHK-03 | TC-CHK-04 to TC-CHK-06 | Covered
REQ-CHEC-04 | Checkout | Shipping Methods | Available shipping methods shown with prices | High | TS-CHK-04 | TC-CHK-07, TC-CHK-08 | Covered
REQ-CHEC-05 | Checkout | Payment Methods | Cash on delivery and other methods work | High | TS-CHK-05 | TC-CHK-09 | Covered
REQ-CHEC-06 | Checkout | Order Confirmation | Order confirmation page and email sent | High | TS-CHK-06 | TC-CHK-10 to TC-CHK-16 | Covered
REQ-ORDE-01 | Orders | Order History | Customer can view past orders with status | High | TS-ORD-01 | TC-ORD-01, TC-ORD-02 | Covered
REQ-ORDE-02 | Orders | Order Detail | Order detail page shows all items and tracking | High | TS-ORD-02 | TC-ORD-03 | Covered
REQ-ORDE-03 | Orders | Order Cancellation | Customer can cancel eligible orders | Medium | TS-ORD-03 | TC-ORD-04, TC-ORD-05 | Covered
REQ-ORDE-04 | Orders | Admin Order Mgmt | Admin can view, update, cancel, invoice orders | High | TS-ORD-04 | TC-ORD-06 to TC-ORD-13 | Covered
REQ-ORDE-05 | Orders | Invoice Generation | Admin generates downloadable PDF invoice | Medium | TS-ORD-05 | TC-ORD-10, TC-ORD-11 | Covered
REQ-ADMI-01 | Admin - Catalog | Add Product | Admin creates simple/configurable/virtual product | High | TS-ADM-CAT-01 | TC-ADM-CAT-01 to TC-ADM-CAT-05 | Covered
REQ-ADMI-02 | Admin - Catalog | Edit Product | Admin edits product details; changes reflect on storefront | High | TS-ADM-CAT-02 | TC-ADM-CAT-06 to TC-ADM-CAT-08 | Covered
REQ-ADMI-03 | Admin - Catalog | Delete Product | Admin deletes product; removed from storefront | Medium | TS-ADM-CAT-03 | TC-ADM-CAT-09 | Covered
REQ-ADMI-04 | Admin - Catalog | Product Images | Multiple images upload and assign to product | Medium | TS-ADM-CAT-04 | TC-ADM-CAT-10, TC-ADM-CAT-11 | Covered
REQ-ADMI-05 | Admin - Catalog | Category Mgmt | Admin creates/edits/deletes categories | High | TS-ADM-CAT-05 | TC-ADM-CAT-12 to TC-ADM-CAT-15 | Covered
REQ-ADMI-06 | Admin - Catalog | Attributes | Create and assign product attributes/attribute sets | Medium | TS-ADM-CAT-06 | TC-ADM-CAT-16 to TC-ADM-CAT-18 | Covered
REQ-USER-01 | User Management | Admin Users | Admin creates/edits sub-admin with roles | Medium | TS-USR-01 | TC-USR-01 to TC-USR-04 | Covered
REQ-USER-02 | User Management | Customer List | Admin views all customers with filters | Medium | TS-USR-02 | TC-USR-05, TC-USR-06, TC-USR-09 | Covered
REQ-USER-03 | User Management | Customer Profile | Admin edits customer info | Medium | TS-USR-03 | TC-USR-07, TC-USR-08, TC-USR-10 | Covered
REQ-ADMI-07 | Admin - Settings | General Config | Store name, currency, locale configurable | High | TS-SET-01 | TC-SET-01 to TC-SET-03, TC-SET-10, TC-SET-11 | Covered
REQ-ADMI-08 | Admin - Settings | Tax Rules | Tax rates applied correctly based on rules | High | TS-SET-02 | TC-SET-04, TC-SET-05 | Covered
REQ-ADMI-09 | Admin - Settings | Shipping Config | Shipping zones and rates configured | High | TS-SET-03 | TC-SET-06, TC-SET-07 | Covered
REQ-ADMI-10 | Admin - Settings | Payment Config | Payment methods enabled/disabled | High | TS-SET-04 | TC-SET-08, TC-SET-09, TC-SET-12 | Covered
REQ-UIUX-01 | UI/UX | Responsive Design | Storefront responsive on mobile, tablet, desktop | High | TS-UI-01 | TC-UI-01 to TC-UI-03, TC-UI-08 | Covered
REQ-UIUX-02 | UI/UX | Navigation | Menu links navigate to correct pages | High | TS-UI-02 | TC-UI-04 to TC-UI-07, TC-UI-09, TC-UI-10 | Covered
REQ-UIUX-03 | UI/UX | Error Pages | 404 and 500 pages display correctly | Medium |  |  | Not Covered
REQ-PERF-01 | Performance | Page Load | Key pages load within acceptable time | Medium | TS-PERF-01 | TC-PERF-01 to TC-PERF-07 | Covered
REQ-PERF-02 | Performance | Search Speed | Product search returns results quickly | Medium |  |  | Not Covered
Total Requirements: | 46
Covered Requirements: | 41
Coverage %: | 89.13%

## Module Overview
# | Module | Description | Scenarios | Test Cases | Priority
1 | Authentication | Login, logout, registration, forgot password | 5 | 16 | High
2 | Product Catalog | Listing, search, filter, sort, detail, reviews | 6 | 18 | High
3 | Shopping Cart | Add, update, remove, persistence, totals | 4 | 12 | High
4 | Checkout | Guest, registered, address, shipping, payment, confirm | 6 | 16 | High
5 | Order Management | History, detail, cancel, status, invoice | 5 | 14 | High
6 | Admin – Catalog | Add/edit/delete products, categories, attributes | 6 | 18 | High
7 | Admin – Orders | View, update status, invoice, shipment | 4 | 12 | High
8 | User Management | Admin users, customer list, customer profile | 3 | 10 | Medium
9 | Admin – Settings | Config, tax, shipping, payment, locale | 4 | 12 | Medium
10 | UI/UX & Navigation | Responsive, menus, error pages, breadcrumbs | 2 | 10 | Medium
11 | Performance | Page load, search speed, bulk operations | 1 | 7 | Low
| TOTAL |  | 46 | 145

## Test Scenarios
TS ID | Module | Sub-Module | Test Scenario | Objective | Priority | Linked TC IDs | Notes
◼ AUTHENTICATION
TS-AUTH-01 | Authentication | Login | Verify login with valid and invalid credentials | Ensure authentication accepts correct creds and rejects wrong ones | High | TC-AUTH-01 to TC-AUTH-05 | Covers admin & customer
TS-AUTH-02 | Authentication | Logout | Verify session ends correctly on logout | User is logged out and cannot access protected pages | High | TC-AUTH-08, TC-AUTH-09, TC-AUTH-16
TS-AUTH-03 | Authentication | Registration | Verify new customer registration | New account created with valid data; duplicates and weak passwords rejected | High | TC-AUTH-10 to TC-AUTH-13
TS-AUTH-04 | Authentication | Forgot Password | Verify password reset flow | Reset email sent for valid emails; error for unknown emails | Medium | TC-AUTH-14, TC-AUTH-15
TS-AUTH-05 | Authentication | Security | Verify login security against injection attacks | SQL injection and session hijack attempts are blocked | High | TC-AUTH-05, TC-AUTH-16 | Security testing
◼ PRODUCT CATALOG
TS-CAT-01 | Product Catalog | Product Listing | Verify products display correctly on storefront | Products shown with correct name, price, and image | High | TC-CAT-01, TC-CAT-02
TS-CAT-02 | Product Catalog | Product Search | Verify search functionality returns correct results | Search by keyword returns matching products; no results shown when no match | High | TC-CAT-03 to TC-CAT-05
TS-CAT-03 | Product Catalog | Product Filter | Verify product filtering narrows results correctly | Filtering by category and price shows only matching products | High | TC-CAT-06 to TC-CAT-09
TS-CAT-04 | Product Catalog | Product Sort | Verify product sorting orders results correctly | Sort by price/name/newest reorders product list as expected | Medium | TC-CAT-10 to TC-CAT-12
TS-CAT-05 | Product Catalog | Product Detail | Verify product detail page shows complete info | All product details, images, and stock status shown correctly | High | TC-CAT-13 to TC-CAT-15
TS-CAT-06 | Product Catalog | Product Reviews | Verify customers can submit and view reviews | Reviews saved and displayed; empty submission blocked | Medium | TC-CAT-16, TC-CAT-17, TC-CAT-18
◼ SHOPPING CART
TS-CART-01 | Shopping Cart | Add to Cart | Verify products can be added to cart | In-stock products added; OOS products blocked | High | TC-CART-01 to TC-CART-04
TS-CART-02 | Shopping Cart | Update Quantity | Verify cart quantity updates work correctly | Qty changes recalculate totals; zero qty handled | High | TC-CART-05 to TC-CART-07
TS-CART-03 | Shopping Cart | Remove Item | Verify items can be removed from cart | Individual and all-item removal works; empty state shown | High | TC-CART-08, TC-CART-09
TS-CART-04 | Shopping Cart | Cart Total | Verify cart totals and tax are calculated correctly | Subtotal and tax match expected values based on qty and rules | High | TC-CART-10 to TC-CART-12
◼ CHECKOUT
TS-CHK-01 | Checkout | Guest Checkout | Verify guest users can complete checkout | Guest places order without creating account | High | TC-CHK-01, TC-CHK-02
TS-CHK-02 | Checkout | Registered Checkout | Verify logged-in users can complete checkout | Registered user places order with saved address | High | TC-CHK-03
TS-CHK-03 | Checkout | Shipping Address | Verify address validation at checkout | Valid address accepted; missing/invalid fields blocked | High | TC-CHK-04 to TC-CHK-06
TS-CHK-04 | Checkout | Shipping Methods | Verify shipping options display and apply correctly | Shipping methods shown; free shipping applied above threshold | High | TC-CHK-07, TC-CHK-08
TS-CHK-05 | Checkout | Payment | Verify payment methods work at checkout | COD and other enabled methods can be selected and order placed | High | TC-CHK-09
TS-CHK-06 | Checkout | Order Confirmation | Verify order confirmation is shown and emailed | Confirmation page and email sent after successful order | High | TC-CHK-10 to TC-CHK-16 | Coupon testing included
◼ ORDER MANAGEMENT
TS-ORD-01 | Order Management | Order History | Verify customers can view their order history | All past orders listed with correct status, date, total | High | TC-ORD-01, TC-ORD-02
TS-ORD-02 | Order Management | Order Detail | Verify order detail shows all correct information | Items, quantities, address, invoice shown in order detail | High | TC-ORD-03
TS-ORD-03 | Order Management | Order Cancellation | Verify eligible orders can be cancelled by customer | Pending orders can be cancelled; shipped orders cannot | Medium | TC-ORD-04, TC-ORD-05
TS-ORD-04 | Order Management | Admin Order Mgmt | Verify admin can manage and update orders | Admin views, filters, updates status, creates shipments | High | TC-ORD-06 to TC-ORD-13
TS-ORD-05 | Order Management | Invoice | Verify admin can generate and verify invoices | PDF invoice generated with correct data for each order | Medium | TC-ORD-10, TC-ORD-11
◼ ADMIN – CATALOG
TS-ADM-CAT-01 | Admin – Catalog | Add Product | Verify admin can create all product types | Simple and configurable products created with correct data | High | TC-ADM-CAT-01 to TC-ADM-CAT-05
TS-ADM-CAT-02 | Admin – Catalog | Edit Product | Verify admin edits reflect on storefront | Price, name, stock changes saved and visible on storefront | High | TC-ADM-CAT-06 to TC-ADM-CAT-08
TS-ADM-CAT-03 | Admin – Catalog | Delete Product | Verify product deletion removes from storefront | Deleted products no longer appear in storefront catalog | Medium | TC-ADM-CAT-09
TS-ADM-CAT-04 | Admin – Catalog | Product Images | Verify product images upload and display correctly | Valid images accepted; invalid file types rejected | Medium | TC-ADM-CAT-10, TC-ADM-CAT-11
TS-ADM-CAT-05 | Admin – Catalog | Category Mgmt | Verify admin can manage product categories | Create/edit/delete/nest categories; navigation updates | High | TC-ADM-CAT-12 to TC-ADM-CAT-15
TS-ADM-CAT-06 | Admin – Catalog | Attributes | Verify product attributes can be created and assigned | Attributes created and visible on product detail page | Medium | TC-ADM-CAT-16 to TC-ADM-CAT-18
◼ ADMIN – ORDERS
TS-ADM-ORD-01 | Admin – Orders | Order View | Verify admin can view and filter all orders | All orders visible; filters by date, status, email work | High | TC-ADM-ORD-01 to TC-ADM-ORD-03
TS-ADM-ORD-02 | Admin – Orders | Shipment | Verify admin can create shipments with tracking | Shipments created; tracking number saved and visible | High | TC-ADM-ORD-04
TS-ADM-ORD-03 | Admin – Orders | Invoice/Refund | Verify admin can invoice and refund orders | Invoice amounts match; credit memo records refund | Medium | TC-ADM-ORD-05, TC-ADM-ORD-07
TS-ADM-ORD-04 | Admin – Orders | Bulk Actions | Verify bulk order operations work correctly | Bulk status update applies to all selected orders | Medium | TC-ADM-ORD-06, TC-ADM-ORD-08, TC-ADM-ORD-09
◼ USER MANAGEMENT
TS-USR-01 | User Management | Admin Users | Verify admin can create and manage sub-admins | Sub-admins created, edited, deleted; RBAC enforced | Medium | TC-USR-01 to TC-USR-04
TS-USR-02 | User Management | Customer List | Verify admin can view and filter customers | Customer list shown; filter by email works; export works | Medium | TC-USR-05, TC-USR-06, TC-USR-09
TS-USR-03 | User Management | Customer Profile | Verify admin can edit and manage customer profiles | Email updated; orders visible; inactive status blocks login | Medium | TC-USR-07, TC-USR-08, TC-USR-10
◼ ADMIN – SETTINGS
TS-SET-01 | Admin – Settings | General Config | Verify store general settings can be configured | Store name, currency, timezone, locale change correctly | High | TC-SET-01 to TC-SET-03, TC-SET-10, TC-SET-11
TS-SET-02 | Admin – Settings | Tax Rules | Verify tax rates are configured and applied | Tax rates created; correct tax applied at checkout | High | TC-SET-04, TC-SET-05
TS-SET-03 | Admin – Settings | Shipping Config | Verify shipping methods are configured correctly | Flat rate and free shipping configured; shown at checkout | High | TC-SET-06, TC-SET-07
TS-SET-04 | Admin – Settings | Payment Config | Verify payment methods can be enabled/disabled | Enabled methods appear at checkout; disabled do not | High | TC-SET-08, TC-SET-09, TC-SET-12
◼ UI/UX
TS-UI-01 | UI/UX | Responsive | Verify storefront is responsive across all screen sizes | No layout breakage on mobile, tablet, desktop | High | TC-UI-01 to TC-UI-03, TC-UI-08
TS-UI-02 | UI/UX | Navigation | Verify all navigation links and UI elements work | Menu links, footer, breadcrumbs, toasts all function correctly | High | TC-UI-04 to TC-UI-07, TC-UI-09, TC-UI-10
◼ PERFORMANCE
TS-PERF-01 | Performance | Page Load | Verify key pages load within acceptable time | Homepage, catalog, checkout, admin load within 3–5 seconds | Medium | TC-PERF-01 to TC-PERF-07 | Local environment

## Test Cases
TC ID | Module | Sub-Module | Test Scenario | Test Case Description | Pre-Conditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Test Type | Bug ID / Notes
◼ AUTHENTICATION
TC-AUTH-01 | Authentication | Login | Valid admin login | Admin logs in with correct creds | App running, admin account exists | 1. Go to /admin 2. Enter email 3. Enter password 4. Click Login | Email: admin@example.com Pass: admin123 | Admin dashboard displayed |  | Pending | High | Functional
TC-AUTH-02 | Authentication | Login | Invalid admin email | Login fails with wrong email | App running | 1. Go to /admin 2. Enter wrong email 3. Enter correct password 4. Click Login | Email: wrong@test.com Pass: admin123 | Error message shown; no login |  | Pending | High | Functional
TC-AUTH-03 | Authentication | Login | Invalid admin pass | Login fails with wrong password | App running | 1. Go to /admin 2. Enter correct email 3. Enter wrong password 4. Click Login | Email: admin@example.com Pass: wrongpass | Error message; no login |  | Pending | High | Functional
TC-AUTH-04 | Authentication | Login | Empty fields | Login fails with empty fields | App running | 1. Go to /admin 2. Leave fields empty 3. Click Login |  | Validation messages for required fields |  | Pending | High | Functional
TC-AUTH-05 | Authentication | Login | SQL injection login | System rejects SQL injection attempt | App running | 1. Go to /admin 2. Enter ' OR 1=1 -- in email 3. Click Login | Email: ' OR 1=1 -- | Login fails; no DB exposure |  | Pending | High | Security
TC-AUTH-06 | Authentication | Login | Customer valid login | Customer logs in with correct creds | Customer account exists | 1. Go to storefront 2. Click Login 3. Enter email & pass 4. Submit | Email: ahnattanha562@gmail.com Pass: 12345678 | Customer account page shown |  | Pending | High | Functional
TC-AUTH-07 | Authentication | Login | Customer invalid pass | Customer login fails with wrong pass | Customer account exists | 1. Go to login 2. Enter valid email, wrong pass 3. Submit | Email: ahnattanha562@gmail.com Pass: wrong | Error: These credentials do not match |  | Pending | High | Functional
TC-AUTH-08 | Authentication | Logout | Admin logout | Admin session ends on logout | Admin logged in | 1. Click account icon in admin 2. Click Logout |  | Redirected to /admin/login |  | Pending | High | Functional
TC-AUTH-09 | Authentication | Logout | Customer logout | Customer session ends on logout | Customer logged in | 1. Click account in header 2. Click Logout |  | Redirected to home/login page |  | Pending | High | Functional
TC-AUTH-10 | Authentication | Registration | Valid registration | New customer registers successfully | No prior account | 1. Go to Register 2. Fill all fields 3. Submit | Name: Test User Email: newuser@test.com Pass: Test@1234 | Account created; redirect to profile |  | Pending | High | Functional
TC-AUTH-11 | Authentication | Registration | Duplicate email | Registration fails for existing email | Existing customer email | 1. Go to Register 2. Enter existing email 3. Submit | Email: ahnattanha562@gmail.com | Error: email already taken |  | Pending | High | Functional
TC-AUTH-12 | Authentication | Registration | Weak password | Registration fails for short password |  | 1. Go to Register 2. Enter password < 6 chars 3. Submit | Pass: 123 | Validation error shown |  | Pending | High | Functional
TC-AUTH-13 | Authentication | Registration | Missing required fields | Registration fails with empty fields |  | 1. Go to Register 2. Leave required fields blank 3. Submit |  | Field-level validation errors shown |  | Pending | Medium | Functional
TC-AUTH-14 | Authentication | Forgot Pass | Valid email reset | Reset email sent for valid email | Registered account | 1. Go to Forgot Password 2. Enter registered email 3. Submit | Email: ahnattanha562@gmail.com | Success message; email sent |  | Pending | Medium | Functional
TC-AUTH-15 | Authentication | Forgot Pass | Invalid email reset | No email sent for unknown email |  | 1. Go to Forgot Password 2. Enter unknown email 3. Submit | Email: fake@notexist.com | Error or generic message shown |  | Pending | Medium | Functional
TC-AUTH-16 | Authentication | Login | Back button after logout | Cannot access dashboard after logout | Logged out | 1. Logout 2. Click browser back button |  | Redirected to login; session expired |  | Pending | High | Security
◼ PRODUCT CATALOG
TC-CAT-01 | Product Catalog | Product Listing | Products display on home | Homepage shows products correctly | App running, products exist | 1. Open storefront URL 2. Observe product grid |  | Products displayed with name, price, image |  | Pending | High | Functional
TC-CAT-02 | Product Catalog | Product Listing | Pagination works | Pagination navigates through pages | Multiple products exist | 1. View product listing 2. Click page 2 3. Observe products |  | Next set of products shown |  | Pending | Medium | Functional
TC-CAT-03 | Product Catalog | Product Search | Search valid keyword | Search returns matching products | Products in DB | 1. Enter product name in search 2. Press Enter | Keyword: shirt | Products matching 'shirt' listed |  | Pending | High | Functional
TC-CAT-04 | Product Catalog | Product Search | Search no results | No results page for unknown keyword |  | 1. Search for non-existent product | Keyword: xyzabc123 | 'No products found' message shown |  | Pending | High | Functional
TC-CAT-05 | Product Catalog | Product Search | Case insensitive search | Search works regardless of case | Products exist | 1. Search 'SHIRT' 2. Search 'shirt' 3. Compare results | Keyword: SHIRT / shirt | Same results returned |  | Pending | Medium | Functional
TC-CAT-06 | Product Catalog | Product Filter | Filter by category | Filtering shows correct category products | Categories with products | 1. Select category from sidebar 2. Observe results | Category: Clothing | Only products in 'Clothing' shown |  | Pending | High | Functional
TC-CAT-07 | Product Catalog | Product Filter | Filter by price range | Price filter limits shown products | Multiple price range products | 1. Set price min/max slider 2. Apply filter | Min: 10, Max: 50 | Products only in $10–$50 shown |  | Pending | High | Functional
TC-CAT-08 | Product Catalog | Product Filter | Multiple filters combined | Combined filters narrow results |  | 1. Select category + price range 2. Observe results | Category: Clothing, Price: 10–50 | Intersection of both filters |  | Pending | High | Functional
TC-CAT-09 | Product Catalog | Product Filter | Clear filter | Clearing filter resets product list | Filter applied | 1. Apply filter 2. Click Clear/Reset |  | All products shown again |  | Pending | Medium | Functional
TC-CAT-10 | Product Catalog | Product Sort | Sort by price low-high | Products sorted ascending by price | Products with different prices | 1. Select Sort: Price Low to High |  | Products ordered cheapest first |  | Pending | Medium | Functional
TC-CAT-11 | Product Catalog | Product Sort | Sort by price high-low | Products sorted descending by price | Products with different prices | 1. Select Sort: Price High to Low |  | Products ordered most expensive first |  | Pending | Medium | Functional
TC-CAT-12 | Product Catalog | Product Sort | Sort by newest | Newest products appear first | Products with different dates | 1. Select Sort: Newest |  | Most recently added product first |  | Pending | Medium | Functional
TC-CAT-13 | Product Catalog | Product Detail | Product page loads | Product detail page shows all info | Product exists | 1. Click on any product |  | Name, price, description, images shown |  | Pending | High | Functional
TC-CAT-14 | Product Catalog | Product Detail | Image gallery | Multiple images viewable in gallery | Product with multiple images | 1. Open product detail 2. Click on thumbnail images |  | Main image changes on click |  | Pending | Medium | UI/UX
TC-CAT-15 | Product Catalog | Product Detail | Out of stock display | Out-of-stock product shows correct label | Out-of-stock product | 1. Open out-of-stock product page |  | 'Out of Stock' shown; Add to Cart disabled |  | Pending | High | Functional
TC-CAT-16 | Product Catalog | Product Reviews | Submit review | Customer submits product review | Customer logged in, product exists | 1. Go to product page 2. Fill review form 3. Submit | Rating: 4, Text: Good quality | Review saved and displayed |  | Pending | Medium | Functional
TC-CAT-17 | Product Catalog | Product Reviews | Empty review blocked | Review fails without rating or text | Customer logged in | 1. Go to product page 2. Leave review form empty 3. Submit |  | Validation error shown |  | Pending | Medium | Functional
TC-CAT-18 | Product Catalog | Category Nav | Category breadcrumb | Breadcrumb reflects correct navigation path | Category hierarchy exists | 1. Navigate to sub-category 2. Observe breadcrumb |  | Correct path shown in breadcrumb |  | Pending | Medium | UI/UX
◼ SHOPPING CART
TC-CART-01 | Shopping Cart | Add to Cart | Add single product | Product added to cart successfully | Product available in stock | 1. Go to product page 2. Click Add to Cart | Product: any in-stock item | Cart icon shows 1 item; success toast |  | Pending | High | Functional
TC-CART-02 | Shopping Cart | Add to Cart | Add multiple products | Multiple different products added | Multiple in-stock products | 1. Add product A 2. Add product B 3. View cart | Product A & B | Cart shows 2 distinct items |  | Pending | High | Functional
TC-CART-03 | Shopping Cart | Add to Cart | Add same product twice | Quantity increases for duplicate add | Product in stock | 1. Add same product twice | Qty: 1 each time | Cart shows qty 2 for that product |  | Pending | High | Functional
TC-CART-04 | Shopping Cart | Add to Cart | Add out-of-stock product | Cannot add out-of-stock product | Out-of-stock product exists | 1. Try to add OOS product to cart |  | Add to Cart disabled or error shown |  | Pending | High | Functional
TC-CART-05 | Shopping Cart | Update Quantity | Increase quantity | Cart total updates when qty increased | Item in cart | 1. View cart 2. Increase qty to 3 3. Update | Qty: 3 | Subtotal recalculated correctly |  | Pending | High | Functional
TC-CART-06 | Shopping Cart | Update Quantity | Decrease quantity | Cart total updates when qty decreased | Item with qty > 1 in cart | 1. View cart 2. Decrease qty to 1 3. Update | Qty: 1 | Subtotal recalculated correctly |  | Pending | High | Functional
TC-CART-07 | Shopping Cart | Update Quantity | Set quantity to zero | Cart item removed or error when qty = 0 | Item in cart | 1. View cart 2. Set qty to 0 3. Update | Qty: 0 | Item removed or validation error |  | Pending | Medium | Functional
TC-CART-08 | Shopping Cart | Remove Item | Remove one item | Item removed from cart | Item in cart | 1. View cart 2. Click Remove on item |  | Item no longer in cart; total updated |  | Pending | High | Functional
TC-CART-09 | Shopping Cart | Remove Item | Remove all items | Cart becomes empty | Items in cart | 1. Remove all items one by one |  | Cart shows empty state message |  | Pending | High | Functional
TC-CART-10 | Shopping Cart | Cart Total | Subtotal calculation | Subtotal = price × quantity | Items in cart | 1. Check product price 2. Set qty 3. View cart total | Price: $20, Qty: 3 | Subtotal = $60.00 |  | Pending | High | Functional
TC-CART-11 | Shopping Cart | Cart Total | Tax applied correctly | Tax amount shown in cart/checkout | Tax rule configured | 1. Add item to cart 2. Proceed to checkout 3. Check tax line | Taxable item | Tax calculated per configured rate |  | Pending | High | Functional
TC-CART-12 | Shopping Cart | Cart Persistence | Cart saved on login | Guest cart items retained after login | Guest cart with items | 1. Add item as guest 2. Login 3. View cart |  | Previously added items still in cart |  | Pending | Medium | Functional
◼ CHECKOUT
TC-CHK-01 | Checkout | Guest Checkout | Guest can checkout | Guest completes order without login | Items in cart | 1. Add item 2. Proceed to checkout 3. Enter guest email & address 4. Select shipping 5. Place order | Email: guest@test.com, valid address | Order placed; confirmation shown |  | Pending | High | Functional
TC-CHK-02 | Checkout | Guest Checkout | Guest checkout email captured | Guest email saved with order | Guest checkout flow | 1. Complete guest checkout 2. Check admin orders | Email: guest@test.com | Email shown in admin order detail |  | Pending | High | Functional
TC-CHK-03 | Checkout | Registered Checkout | Logged-in user checkout | Registered user completes order | Customer logged in, cart with items | 1. Add item 2. Proceed to checkout 3. Select saved address 4. Place order | Saved address | Order placed; confirmation page shown |  | Pending | High | Functional
TC-CHK-04 | Checkout | Shipping Address | Valid address accepted | Checkout proceeds with valid address | Checkout page | 1. Enter full valid address 2. Continue | Name, Street, City, ZIP, Country | Address accepted; move to shipping step |  | Pending | High | Functional
TC-CHK-05 | Checkout | Shipping Address | Missing required address field | Checkout blocked when address incomplete | Checkout page | 1. Leave City field empty 2. Click Continue | Missing: City | Validation error on City field |  | Pending | High | Functional
TC-CHK-06 | Checkout | Shipping Address | Invalid ZIP code | Checkout shows error for invalid ZIP | Checkout page | 1. Enter invalid ZIP 2. Continue | ZIP: ABCDE | Validation error or warning shown |  | Pending | Medium | Functional
TC-CHK-07 | Checkout | Shipping Methods | Shipping options displayed | Available shipping methods shown | Shipping configured | 1. Reach shipping step in checkout |  | At least one shipping method listed with price |  | Pending | High | Functional
TC-CHK-08 | Checkout | Shipping Methods | Free shipping threshold | Free shipping applied above threshold | Free shipping configured e.g. > $100 | 1. Add items totaling > $100 2. Reach shipping step | Cart total > $100 | Free Shipping option shown ($0.00) |  | Pending | High | Functional
TC-CHK-09 | Checkout | Payment Methods | Cash on delivery | COD payment option available and selectable | COD enabled in settings | 1. Reach payment step 2. Select COD 3. Place order | Payment: COD | Order placed; COD shown in confirmation |  | Pending | High | Functional
TC-CHK-10 | Checkout | Order Confirmation | Confirmation page shown | Order confirmation page loads after order | Completed checkout | 1. Place order successfully |  | Confirmation page with order ID shown |  | Pending | High | Functional
TC-CHK-11 | Checkout | Order Confirmation | Confirmation email sent | Customer receives order email | Completed checkout, mail configured | 1. Place order 2. Check inbox | Customer email | Confirmation email with order summary received |  | Pending | High | Functional
TC-CHK-12 | Checkout | Checkout | Empty cart checkout blocked | Cannot proceed to checkout with empty cart | No items in cart | 1. Go to checkout URL directly |  | Redirected to cart or error shown |  | Pending | Medium | Functional
TC-CHK-13 | Checkout | Checkout | Coupon code valid | Discount applied with valid coupon | Coupon created in admin | 1. Add item 2. At checkout enter coupon 3. Apply | Coupon: TEST10 | Discount reflected in order total |  | Pending | High | Functional
TC-CHK-14 | Checkout | Checkout | Coupon code invalid | Error shown for invalid coupon | Checkout page | 1. Enter invalid coupon 2. Apply | Coupon: FAKE99 | Error: Coupon not found/expired |  | Pending | Medium | Functional
TC-CHK-15 | Checkout | Checkout | Multiple shipping addresses | User selects from multiple saved addresses | Registered user with 2+ addresses | 1. Reach address step 2. Select non-default address | Address 2 | Selected address used in order |  | Pending | Medium | Functional
TC-CHK-16 | Checkout | Checkout | Order total matches cart | Checkout total equals cart summary | Cart with items | 1. Note cart total 2. Proceed to checkout 3. Compare totals |  | Checkout total = Cart total (same items, same price) |  | Pending | High | Functional
◼ ORDER MANAGEMENT
TC-ORD-01 | Order Management | Order History | Customer views order history | All placed orders listed in account | Customer has placed orders | 1. Login 2. Go to My Account > Orders |  | All orders listed with ID, date, status, total |  | Pending | High | Functional
TC-ORD-02 | Order Management | Order History | Order history pagination | Pagination works in order list | Customer with many orders | 1. View Orders page 2. Navigate pages |  | Correct orders per page |  | Pending | Medium | Functional
TC-ORD-03 | Order Management | Order Detail | Customer views order detail | Order detail shows correct items | Order exists | 1. Click order in history 2. View detail |  | Items, quantities, prices, address shown |  | Pending | High | Functional
TC-ORD-04 | Order Management | Order Cancellation | Cancel pending order | Customer cancels pending order | Order in Pending status | 1. Open order detail 2. Click Cancel Order 3. Confirm |  | Order status changes to Cancelled |  | Pending | Medium | Functional
TC-ORD-05 | Order Management | Order Cancellation | Cannot cancel shipped order | Cancel not available for shipped orders | Order in Shipped status | 1. Open shipped order 2. Observe Cancel option |  | Cancel button absent or disabled |  | Pending | Medium | Functional
TC-ORD-06 | Order Management | Admin Order Mgmt | Admin views all orders | Admin sees all customer orders | Admin logged in | 1. Go to Admin > Sales > Orders |  | All orders listed in admin panel |  | Pending | High | Functional
TC-ORD-07 | Order Management | Admin Order Mgmt | Admin filters orders by status | Filter shows only matching status orders | Admin panel | 1. Apply status filter: Pending | Status: Pending | Only pending orders shown |  | Pending | High | Functional
TC-ORD-08 | Order Management | Admin Order Mgmt | Admin updates order status | Admin changes order status | Order in Pending status | 1. Open admin order 2. Change status to Processing 3. Save | Status: Processing | Order status updated; customer notified |  | Pending | High | Functional
TC-ORD-09 | Order Management | Admin Order Mgmt | Admin creates shipment | Shipment created for order | Order in Processing | 1. Open admin order 2. Click Ship 3. Confirm |  | Shipment created; status updates to Shipped |  | Pending | High | Functional
TC-ORD-10 | Order Management | Invoice Generation | Admin generates invoice | PDF invoice generated for order | Order exists in admin | 1. Open admin order 2. Click Invoice 3. Generate |  | Invoice PDF generated and downloadable |  | Pending | Medium | Functional
TC-ORD-11 | Order Management | Invoice Generation | Invoice shows correct data | Invoice PDF has correct order data | Invoice generated | 1. Open invoice PDF 2. Verify data |  | Customer name, items, total, date correct |  | Pending | Medium | Functional
TC-ORD-12 | Order Management | Admin Order Mgmt | Admin search order by ID | Admin can find order by ID | Orders in system | 1. Enter order ID in search 2. Submit | Order ID: 1 | Matching order displayed |  | Pending | Medium | Functional
TC-ORD-13 | Order Management | Admin Order Mgmt | Admin refund/cancel order | Admin cancels order from backend | Order in pending/processing | 1. Open order in admin 2. Cancel the order |  | Order cancelled; stock restored |  | Pending | Medium | Functional
TC-ORD-14 | Order Management | Order History | Order status visible to customer | Customer sees updated status | Admin updated order status | 1. Admin update status 2. Customer views order |  | Customer sees new status in My Orders |  | Pending | High | Functional
◼ ADMIN - CATALOG
TC-ADM-CAT-01 | Admin - Catalog | Add Product | Add simple product | Admin creates a new simple product | Admin logged in | 1. Go to Catalog > Products 2. Click Add Product 3. Fill details 4. Save | Name: Test Shirt Price: $29.99 SKU: TSH001 | Product saved and visible in storefront |  | Pending | High | Functional
TC-ADM-CAT-02 | Admin - Catalog | Add Product | Add product without name | Product creation fails without name | Admin logged in | 1. Go to Add Product 2. Leave name blank 3. Save | Name: (empty) | Validation error on Name field |  | Pending | High | Functional
TC-ADM-CAT-03 | Admin - Catalog | Add Product | Add product without price | Product creation fails without price | Admin logged in | 1. Go to Add Product 2. Leave price blank 3. Save | Price: (empty) | Validation error on Price field |  | Pending | High | Functional
TC-ADM-CAT-04 | Admin - Catalog | Add Product | Add product with negative price | Negative price rejected | Admin logged in | 1. Enter price: -10 2. Save | -10 | Validation error; negative price not allowed |  | Pending | Medium | Functional
TC-ADM-CAT-05 | Admin - Catalog | Add Product | Add configurable product | Admin creates product with variants | Admin logged in | 1. Add Product > Configurable 2. Set attributes (Size) 3. Configure variants 4. Save | Sizes: S, M, L | Product saved with 3 variants in storefront |  | Pending | High | Functional
TC-ADM-CAT-06 | Admin - Catalog | Edit Product | Edit product name | Admin edits product name; storefront updates | Product exists | 1. Go to edit product 2. Change name 3. Save | New name: Updated Shirt | New name shown in storefront |  | Pending | High | Functional
TC-ADM-CAT-07 | Admin - Catalog | Edit Product | Edit product price | Admin edits product price; storefront updates | Product exists | 1. Edit product 2. Change price to $39.99 3. Save | Price: $39.99 | New price shown in storefront |  | Pending | High | Functional
TC-ADM-CAT-08 | Admin - Catalog | Edit Product | Update product stock | Stock quantity updated in admin | Product exists | 1. Edit product 2. Set qty: 50 3. Save | Qty: 50 | Stock updated; product shows in stock |  | Pending | High | Functional
TC-ADM-CAT-09 | Admin - Catalog | Delete Product | Delete product | Admin deletes product; removed from storefront | Product exists | 1. Go to Products 2. Select product 3. Delete 4. Confirm |  | Product removed from storefront and admin list |  | Pending | Medium | Functional
TC-ADM-CAT-10 | Admin - Catalog | Product Images | Upload product image | Admin uploads image for product | Product exists | 1. Edit product 2. Upload image file 3. Save | Image: product.jpg (< 2MB) | Image shown on product page |  | Pending | High | Functional
TC-ADM-CAT-11 | Admin - Catalog | Product Images | Upload invalid file type | System rejects non-image file | Admin editing product | 1. Try uploading PDF as product image | File: doc.pdf | Error: invalid file type |  | Pending | Medium | Functional
TC-ADM-CAT-12 | Admin - Catalog | Category Mgmt | Create category | Admin creates new category | Admin logged in | 1. Go to Catalog > Categories 2. Add New 3. Fill name 4. Save | Category: Summer Sale | Category appears in admin and storefront |  | Pending | High | Functional
TC-ADM-CAT-13 | Admin - Catalog | Category Mgmt | Edit category name | Admin renames category; navigation updates | Category exists | 1. Edit category 2. Change name 3. Save | New name: Winter Collection | Updated name in navigation |  | Pending | Medium | Functional
TC-ADM-CAT-14 | Admin - Catalog | Category Mgmt | Delete category | Admin deletes category; products unassigned | Category with products | 1. Delete category 2. Confirm |  | Category removed; products reassigned or uncategorized |  | Pending | Medium | Functional
TC-ADM-CAT-15 | Admin - Catalog | Category Mgmt | Create sub-category | Admin creates child under parent category | Parent category exists | 1. Add category 2. Set parent: Clothing 3. Name: Men | Parent: Clothing, Child: Men | Sub-category visible under parent in nav |  | Pending | Medium | Functional
TC-ADM-CAT-16 | Admin - Catalog | Attributes | Create attribute | Admin creates product attribute | Admin logged in | 1. Go to Catalog > Attributes 2. Add New 3. Name: Color 4. Type: Select 5. Save | Attribute: Color (Select) | Attribute available in product creation |  | Pending | Medium | Functional
TC-ADM-CAT-17 | Admin - Catalog | Attributes | Assign attribute to product | Attribute assigned and visible on product | Attribute exists | 1. Edit product 2. Select attribute set with Color 3. Set value: Red 4. Save | Color: Red | Product detail shows 'Color: Red' |  | Pending | Medium | Functional
TC-ADM-CAT-18 | Admin - Catalog | Add Product | Duplicate SKU rejected | Two products cannot share SKU | One product with SKU exists | 1. Add new product 2. Enter same SKU 3. Save | SKU: TSH001 | Error: SKU already exists |  | Pending | Medium | Functional
◼ ADMIN - ORDERS
TC-ADM-ORD-01 | Admin - Orders | Order View | Admin dashboard order count | Dashboard shows correct pending order count | Orders in system | 1. Login admin 2. View dashboard widgets |  | Pending orders count is accurate |  | Pending | High | Functional
TC-ADM-ORD-02 | Admin - Orders | Order View | Filter orders by date range | Admin filters orders by date | Orders exist | 1. Set date from–to 2. Apply filter | Date: last 7 days | Only orders in that range shown |  | Pending | Medium | Functional
TC-ADM-ORD-03 | Admin - Orders | Order View | Filter orders by customer | Admin finds orders for specific customer | Orders exist | 1. Search by customer email | Email: ahnattanha562@gmail.com | Orders by that customer listed |  | Pending | Medium | Functional
TC-ADM-ORD-04 | Admin - Orders | Shipment | Create shipment with tracking | Admin adds tracking number to shipment | Order in Processing | 1. Open order 2. Create shipment 3. Add tracking number | Tracking: TRK123456 | Shipment saved with tracking number |  | Pending | High | Functional
TC-ADM-ORD-05 | Admin - Orders | Invoice | Invoice amount correct | Invoice total matches order total | Order with invoice | 1. Open admin order 2. Create invoice 3. View invoice |  | Invoice total = Order total |  | Pending | High | Functional
TC-ADM-ORD-06 | Admin - Orders | Order View | Export orders list | Admin exports orders to CSV/Excel | Admin panel | 1. Go to Orders 2. Select export option |  | CSV/Excel file downloaded with order data |  | Pending | Medium | Functional
TC-ADM-ORD-07 | Admin - Orders | Refund | Admin creates credit memo | Admin refunds order via credit memo | Invoiced order | 1. Open invoiced order 2. Create Credit Memo 3. Confirm |  | Credit memo created; refund recorded |  | Pending | Medium | Functional
TC-ADM-ORD-08 | Admin - Orders | Order Notes | Add comment to order | Admin adds internal note to order | Order in admin | 1. Open order 2. Add comment: 'Called customer' 3. Save | Comment: Called customer | Comment saved and visible in order history |  | Pending | Low | Functional
TC-ADM-ORD-09 | Admin - Orders | Order View | Bulk status update | Admin updates multiple orders at once | Multiple orders exist | 1. Select 3 orders 2. Bulk action: Cancel 3. Submit | 3 selected orders | All 3 orders updated to Cancelled |  | Pending | Medium | Functional
TC-ADM-ORD-10 | Admin - Orders | Order View | Order detail shows full info | All order fields visible in admin detail | Order exists | 1. Open order in admin |  | Customer info, items, totals, shipping, payment shown |  | Pending | High | Functional
TC-ADM-ORD-11 | Admin - Orders | Email Notification | Admin sends order email | Admin re-sends order confirmation | Order exists | 1. Open order 2. Send email: Order Confirmation |  | Email sent to customer |  | Pending | Low | Functional
TC-ADM-ORD-12 | Admin - Orders | Order View | Order search by email | Admin searches orders by customer email | Orders exist | 1. Enter customer email in search | Email: ahnattanha562@gmail.com | Matching orders displayed |  | Pending | Medium | Functional
◼ USER MANAGEMENT
TC-USR-01 | User Management | Admin Users | Create sub-admin | Admin creates a new admin user | Super admin logged in | 1. Go to Settings > Users 2. Add User 3. Fill details 4. Assign role 5. Save | Name: SubAdmin Email: sub@admin.com Role: Manager | Sub-admin account created; can login |  | Pending | Medium | Functional
TC-USR-02 | User Management | Admin Users | Edit admin user role | Admin role changed to lower permission | Sub-admin exists | 1. Edit sub-admin 2. Change role to Viewer 3. Save | Role: Viewer | Role updated; permissions reduced |  | Pending | Medium | Functional
TC-USR-03 | User Management | Admin Users | Delete admin user | Admin user deleted | Sub-admin exists | 1. Select sub-admin 2. Delete 3. Confirm |  | User removed; cannot login |  | Pending | Medium | Functional
TC-USR-04 | User Management | Admin Users | Role-based access control | Sub-admin cannot access unauthorized sections | Sub-admin with limited role logged in | 1. Login as sub-admin 2. Try to access restricted section |  | Access denied or section not visible |  | Pending | High | Security
TC-USR-05 | User Management | Customer List | Admin views customer list | All registered customers listed | Customers registered | 1. Go to Admin > Customers |  | List with name, email, order count shown |  | Pending | Medium | Functional
TC-USR-06 | User Management | Customer List | Filter customer by email | Customer found by email search | Customers in DB | 1. Enter email in customer search | Email: ahnattanha562@gmail.com | Matching customer shown |  | Pending | Medium | Functional
TC-USR-07 | User Management | Customer Profile | Edit customer email | Admin updates customer email | Customer exists | 1. Open customer profile 2. Change email 3. Save | Email: newemail@test.com | Customer email updated |  | Pending | Medium | Functional
TC-USR-08 | User Management | Customer Profile | View customer order history | Admin sees customer's orders in profile | Customer with orders | 1. Open customer profile 2. View orders tab |  | Customer's orders listed |  | Pending | Medium | Functional
TC-USR-09 | User Management | Customer List | Export customer list | Admin exports customer data | Customers in DB | 1. Go to Customers 2. Export |  | CSV with customer data downloaded |  | Pending | Low | Functional
TC-USR-10 | User Management | Customer Profile | Admin disables customer | Disabled customer cannot login | Customer account active | 1. Edit customer 2. Set status: Inactive 3. Save | Status: Inactive | Customer cannot login; error shown |  | Pending | Medium | Functional
◼ ADMIN - SETTINGS
TC-SET-01 | Admin - Settings | General Config | Change store name | Store name updated site-wide | Admin logged in | 1. Go to Settings > General 2. Change store name 3. Save | Store name: MyShop | New name appears in storefront header/title |  | Pending | High | Functional
TC-SET-02 | Admin - Settings | General Config | Change default currency | Currency symbol updated | Admin logged in | 1. Go to Settings > Currency 2. Set default: EUR 3. Save | Currency: EUR | Prices show in EUR on storefront |  | Pending | High | Functional
TC-SET-03 | Admin - Settings | General Config | Change timezone | Timezone updates for store operations | Admin logged in | 1. Go to Settings > General 2. Change timezone 3. Save | Timezone: Asia/Dhaka | Orders use new timezone for timestamps |  | Pending | Medium | Functional
TC-SET-04 | Admin - Settings | Tax Rules | Add tax rate | Tax rate created and applied | Admin logged in | 1. Go to Tax > Tax Rates 2. Add Rate 15% 3. Save 4. Assign to tax rule | Rate: 15% for BD | Tax applied on checkout for BD orders |  | Pending | High | Functional
TC-SET-05 | Admin - Settings | Tax Rules | Zero tax rate | 0% tax shows no tax charge | Tax rule set to 0% | 1. Configure 0% tax 2. Place order | Rate: 0% | No tax shown in checkout |  | Pending | Medium | Functional
TC-SET-06 | Admin - Settings | Shipping Config | Add flat rate shipping | Flat rate shipping created | Admin logged in | 1. Go to Shipping > Flat Rate 2. Enable 3. Set price: $5 4. Save | Price: $5 | Flat Rate $5 shown at checkout |  | Pending | High | Functional
TC-SET-07 | Admin - Settings | Shipping Config | Free shipping threshold | Free shipping above order amount | Admin logged in | 1. Enable Free Shipping 2. Set min order: $100 3. Save | Min: $100 | Free shipping shown when cart > $100 |  | Pending | High | Functional
TC-SET-08 | Admin - Settings | Payment Config | Enable Cash on Delivery | COD payment method active | Admin logged in | 1. Go to Payment 2. Enable COD 3. Save |  | COD option available at checkout |  | Pending | High | Functional
TC-SET-09 | Admin - Settings | Payment Config | Disable payment method | Disabled method not shown at checkout | Payment method enabled | 1. Disable COD in settings 2. Attempt checkout |  | COD option not shown at checkout |  | Pending | Medium | Functional
TC-SET-10 | Admin - Settings | General Config | Enable/disable maintenance mode | Storefront shows maintenance when enabled | Admin logged in | 1. Enable maintenance mode 2. Visit storefront |  | Maintenance page shown to visitors |  | Pending | Medium | Functional
TC-SET-11 | Admin - Settings | General Config | Locale language change | Storefront language changes | Locale enabled | 1. Switch locale to French 2. View storefront | Locale: fr | Storefront text in French |  | Pending | Medium | Functional
TC-SET-12 | Admin - Settings | Email Config | Test email sending | Admin tests email configuration | SMTP configured | 1. Go to Email Settings 2. Send test email | Email: ahnattanha562@gmail.com | Test email received in inbox |  | Pending | Medium | Functional
◼ UI/UX
TC-UI-01 | UI/UX | Responsive | Mobile storefront layout | Storefront renders properly on mobile |  | 1. Open storefront on 375px screen 2. Check layout | Screen: 375px (iPhone SE) | No horizontal scroll; usable UI |  | Pending | High | UI/UX
TC-UI-02 | UI/UX | Responsive | Tablet storefront layout | Storefront renders properly on tablet |  | 1. Open on 768px screen | Screen: 768px | Correct two-column layout |  | Pending | High | UI/UX
TC-UI-03 | UI/UX | Responsive | Desktop storefront | Storefront renders properly on desktop |  | 1. Open on 1440px screen | Screen: 1440px | Full layout with sidebar visible |  | Pending | High | UI/UX
TC-UI-04 | UI/UX | Navigation | Main menu links work | All header navigation links correct |  | 1. Click each main menu item 2. Verify destination |  | Correct pages loaded for each link |  | Pending | High | UI/UX
TC-UI-05 | UI/UX | Navigation | Footer links work | All footer links navigate correctly |  | 1. Click each footer link |  | Each link goes to correct page |  | Pending | Medium | UI/UX
TC-UI-06 | UI/UX | Error Pages | 404 page shown | Custom 404 page for invalid URL |  | 1. Navigate to /nonexistentpage | URL: /thispagedoesnotexist | 404 error page shown with return link |  | Pending | Medium | UI/UX
TC-UI-07 | UI/UX | Navigation | Admin sidebar navigation | Admin panel sidebar links work | Admin logged in | 1. Click each sidebar menu item |  | Correct admin pages loaded |  | Pending | High | UI/UX
TC-UI-08 | UI/UX | Responsive | Admin panel mobile view | Admin panel usable on mobile |  | 1. Open admin on 375px device | Screen: 375px | Admin panel accessible with hamburger menu |  | Pending | Medium | UI/UX
TC-UI-09 | UI/UX | Navigation | Breadcrumb navigation | Breadcrumbs show correct path | Category and product pages | 1. Navigate to product via category 2. Observe breadcrumb |  | Home > Category > Product Name shown |  | Pending | Medium | UI/UX
TC-UI-10 | UI/UX | UI Elements | Success/Error toasts | Toast notifications show for actions |  | 1. Add item to cart 2. Observe notification |  | Green success toast shown briefly |  | Pending | Medium | UI/UX
◼ PERFORMANCE
TC-PERF-01 | Performance | Page Load | Homepage load time | Homepage loads under 3 seconds | App running locally | 1. Open homepage 2. Check DevTools Network tab |  | Page fully loaded < 3 seconds |  | Pending | Medium | Performance
TC-PERF-02 | Performance | Page Load | Product listing page load | Product list loads under 3 seconds | Products in DB | 1. Open /products 2. Check load time |  | Page loads < 3 seconds |  | Pending | Medium | Performance
TC-PERF-03 | Performance | Page Load | Product detail page load | Product detail loads under 3 seconds | Product with images | 1. Open product detail 2. Check load time |  | Page loads < 3 seconds |  | Pending | Medium | Performance
TC-PERF-04 | Performance | Page Load | Admin dashboard load | Admin dashboard loads under 5 seconds | Admin logged in | 1. Login admin 2. Time dashboard load |  | Dashboard loads < 5 seconds |  | Pending | Medium | Performance
TC-PERF-05 | Performance | Search Speed | Search response time | Product search results return quickly | Multiple products | 1. Type keyword in search 2. Note response time | Keyword: shirt | Results shown within 2 seconds |  | Pending | Medium | Performance
TC-PERF-06 | Performance | Page Load | Checkout page load | Checkout page loads quickly | Items in cart | 1. Open checkout 2. Note load time |  | Checkout loads < 3 seconds |  | Pending | Medium | Performance
TC-PERF-07 | Performance | Page Load | Cart page load | Cart loads correctly with items | Items in cart | 1. Open cart page 2. Note load time |  | Cart page loads < 2 seconds |  | Pending | Low | Performance

## Bug Report
Bug ID | TC ID | Module | Bug Title | Severity | Priority | Environment | Steps to Reproduce | Expected Result | Actual Result | Screenshot/Evidence | Reported By | Reported Date | Status | Assigned To | Fixed Date | Remarks
BUG-001 | TC-AUTH-02 | Authentication | Login error message not specific enough | Minor | Medium | Local - Win 11 | 1. Go to /admin 2. Enter wrong email 3. Click Login | Specific error like 'Email not found' | Generic 'Invalid credentials' shown |  | SQA Engineer | 2025-01-01 | Open | Dev Team |  | Consider more specific error messages
BUG-002 | TC-CART-07 | Shopping Cart | Setting qty to 0 causes page error | Major | High | Local - Win 11 | 1. Add item to cart 2. Set qty = 0 3. Click Update | Item removed or validation error shown | 500 server error page shown | screenshot_bug002.png | SQA Engineer | 2025-01-02 | Open | Dev Team |  | Needs input validation on cart qty
BUG-003 | TC-CAT-15 | Product Catalog | Out-of-stock product can still be added to cart | Critical | High | Local - Win 11 | 1. Find out-of-stock product 2. Add to cart | Add to Cart disabled or error message | Product added to cart successfully | screenshot_bug003.png | SQA Engineer | 2025-01-02 | Open | Dev Team |  | Stock validation missing on add-to-cart action

## Test Summary Report
TEST SUMMARY REPORT – BAGISTO 2.4
Project | Bagisto 2.4 E-commerce Platform
Report Date | 2025-01-02
Prepared By | SQA Engineer
Test Cycle | Cycle 1 – Functional Regression
Module-wise Execution Summary
Module | Scenarios | Total TCs | Passed | Failed | Pending / Not Run | Pass Rate
Authentication | 5 | 16 | 0 | 0 | 16 | 0
Product Catalog | 6 | 18 | 0 | 0 | 18 | 0
Shopping Cart | 4 | 12 | 0 | 0 | 12 | 0
Checkout | 6 | 16 | 0 | 0 | 16 | 0
Order Management | 5 | 14 | 0 | 0 | 14 | 0
Admin – Catalog | 6 | 18 | 0 | 0 | 18 | 0
Admin – Orders | 4 | 12 | 0 | 0 | 12 | 0
User Management | 3 | 10 | 0 | 0 | 10 | 0
Admin – Settings | 4 | 12 | 0 | 0 | 12 | 0
UI/UX & Navigation | 2 | 10 | 0 | 0 | 10 | 0
Performance | 1 | 7 | 0 | 0 | 7 | 0
TOTAL | 46 | 145 | 0 | 0 | 145 | 0
Pass Rate: | 0
Defect Summary
Severity | Open | Closed | Total
Critical | 1 | 0 | 1
Major | 1 | 0 | 1
Minor | 1 | 0 | 1
Trivial | 0 | 0 | 0
Total | 3 | 0 | 3
Overall Conclusion & Recommendation
Testing covered 46 requirements across 11 modules via 46 test scenarios and 155 test cases. Execution status, pass rate, and defect counts are tracked above and should be updated as each cycle completes. Based on the defect summary, the project lead should confirm whether exit criteria (no open Critical/High defects, ≥95% High-priority pass rate) have been met before sign-off.
Sign-off
QA Lead: ____________________ Date: __________
Project Manager: ____________________ Date: __________